## ProjeX Parameters (hidden)
8 | Example Project |  | 2004-07-21 13:12 | FALSE | [9 empty] | 15 |  | Username Mike Witcombe | Language code is 1 |  | test_string has been set to local =IF((RC[2]=0),RC[-1],(RC[-1]+RC[2]-1)) | R
9 | 0 | 97.1 | 2004-07-20 13:01 | TRUE | [9 empty] | 13 |  | Company name | 0 | local =IF((RC[2]=0),RC[-1],(RC[-1]+RC[2]-1)) |  | [
0 | 0 | 0 |  | 0 | FALSE | [8 empty] | 15 |  | Computer COMPAQ2 | 3 | local =IF((RC[-2]=0),0,(RC[-2]-RC[-3]+1)) | Lan_Sep is , | ]
47 | [13 empty] | 13 |  |  |  |  | Part_string is ,(RC[-1]+RC[2]-1)) | C
17 | [13 empty] | 27 |  |  |  |  | Found , : ,
2004-07-20 | [13 empty] | 3 |  |  | 0 | local =MIN(R[7]C:R[13]C)
2004-07-26 | TRUE | FALSE | TRUE |  |  | TRUE | [7 empty] | 2 |  |  | 0 | local =MAX(R[6]C:R[12]C[1])
2004-09-10 | 16776960 | TRUE |  |  |  | TRUE | [12 empty] | local ROW is =ROW(RC[2])
FALSE | 255 |  |  |  |  | TRUE |  |  | 2 | [9 empty] | 0
TRUE | TRUE | TRUE | TRUE |  | FALSE | FALSE | Project | FALSE | Sheet1 | 9 | 9 | 0 | 1 | 0 | 0 |  |  |  | local ROW is =SUM(RC[2]:RC[3])
FALSE | FALSE | FALSE | FALSE |  | TRUE | TRUE | Starting Date | FALSE | Initial Proposal | 10 | 9 | 1 | 1 | 0 | 2
FALSE | FALSE | 0 | FALSE |  | FALSE | FALSE | Completion Date | FALSE
FALSE | TRUE |  | TRUE |  |  |  | Present Date | TRUE
0 | FALSE |  | TRUE |  |  |  | Task | FALSE
FALSE | FALSE | FALSE |  |  |  |  | Description | 0
FALSE | FALSE | [5 empty] | Starting
7 | 255 | TRUE |  |  |  | Time | Date
1 | 16711680 | FALSE |  |  |  | Time | Ending
-1 | 0 | 38182 |  |  |  | Hours | Date
-1 | 16776960 | 38196 |  |  |  | Date | %
-1 | 1 |  |  |  |  | Date | Comp.
-1 | 1.001 | We have a dot |  |  |  | Days | No. of
-1 | TRUE | [5 empty] | Days
| TRUE | TRUE |  |  |  |  | Project Milestone
|  | 2026-07-30 20:24 |  |  |  |  | Uncompleted part of task
Completed part of task
Overdue part of task
1234567890123456789012345678901234567890123456789012345678901234567890123456789012345678901234567890123456789012345678901234567890 | 1234567890123456789012345678901234567890123456789012345678901234567890123456789012345678901234567890123456789012345678901234567890 | 0 |  |  |  |  | Legend

## Initial Proposal_PTs (hidden)
1
1
1
1
1
1
1
1
1
|  | 1 | 0 | 0
2004-07-26 | 2004-07-26 | 1 | 0 | 0
2004-07-27 | 2004-07-27 | 1 | 0 | 0
2004-07-28 | 2004-07-31 | 1 | 2 | 2
2004-08-03 | 2004-08-04 | 1 | 0 | 0
2004-07-26 13:01 | 2004-07-28 13:01 | 1 | 0 | 0
2004-07-28 | 2004-07-31 | 1 | 2 | 2
2004-08-05 | 2004-08-05 | 1 | 0 | 0
2004-08-06 | 2004-08-07 |  | 2 | 2
2004-08-10 | 2004-08-13 |  | 0 | 0
2004-08-14 | 2004-08-16 |  | 2 | 2
38218 | 38221 |  | 2 | 2
38224 | 38225 |  | 0 | 0
38205 | 38212 |  | 0 | 0
38226 | 38233 |  | 4 | 4
38238 | 38239 |  | 0 | 0
38240 | 38240 |  | 0 | 0

## Sheet1_PTs (hidden)
1
1
1
1
1
1
1
1
1
|  | 1 | 0
2004-07-15 13:01 | 2004-07-18 13:01 | 1 | 0
2004-07-19 13:01 | 2004-07-19 13:01 |  | 0
2004-07-20 13:01 | 2004-07-21 13:01 |  | 0
2004-07-22 13:01 | 2004-07-25 13:01 |  | 0
2004-07-26 13:01 | 2004-07-28 13:01 |  | 0
2004-07-29 13:01 | 2004-08-01 13:01 |  | 0
2004-08-02 13:01 | 2004-08-03 13:01 |  | 0
2004-08-04 13:01 | 2004-08-11 13:01 |  | 0
2004-08-12 13:01 | 2004-08-13 13:01 |  | 0
2004-08-14 13:01 | 2004-08-14 13:01 |  | 0

## Initial Proposal_PS (hidden)
18 | 28 | 3 | b
1 | 15 | 1 | 0
2 | 17 | 1 | 0 | 3 | 1 | 0
1 | 4 | 1 | 0
1 | 5 | 1 | 0
1 | 6 | 1 | 0
1 | 7 | 1 | 0
1 | 8 | 1 | 0
1 | 9 | 1 | 0
1 | 10 | 1 | 0
1 | 11 | 1 | 0
0
1 | 14 | 1 | 0
1 | 15 | 1 | 0
1 | 16 | 1 | 0
Note on A1: Last row in this sheet with a pointer
Note on A2: Number of preceders allocated to this task(pointer)
Note on B2: Pointer number of the task allocated to this task(pointer)
Note on C2: Lag (currently in days) after the preceeder
Note on D1: Version of Preceed format
Note on D2: Type of lag, 0 : from the end ; 1 : From the start

## Sheet1_PS (hidden)
12 | b
0
0
0
0
0
0
0
0
0
0
Note on A1: Last row in this sheet with a pointer
Note on A2: Number of preceders allocated to this task(pointer)
Note on B2: Pointer number of the task allocated to this task(pointer)
Note on C2: Lag (currently in days) after the preceeder
Note on D1: Version of Preceed format
Note on D2: Type of lag, 0 : from the end ; 1 : From the start

## Initial Proposal_DS (hidden)
18 |  |  | b
1 | 4 | -1 | 0
1 | 5 | -1 | 0
1 | 6 | -1 | 0
1 | 7 | -1 | 0
1 | 8 | -1 | 0
1 | 9 | -1 | 0
1 | 10 | -1 | 0
1 | 11 | -1 | 0
1 | 12 | -1 | 0
0
1 | 15 | -1 | 0
2 | 16 | -1 | 0 | 3 | -1 | 0
1 | 17 | -1 | 0
1 | 4 | -1 | 0

## Sheet1_DS (hidden)
12 | b
0
0
0
0
0
0
0
0
0
0

## Initial Proposal_CS (hidden)
1
Note on A1: Last row in this sheet with a task
Note on A2: Location of task in ProjeX sheet
Note on B1: Starting date of Project
Note on B2: Task start
Note on C1: Ending date of Project
Note on C2: Task end
Note on D2: Task duration
Note on E2: Earliest start
Note on F2: Latest start
Note on G2: Earliest finish
Note on H2: Latest finish
Note on I2: Float

## Sheet1_CS (hidden)
1
Note on A1: Last row in this sheet with a task
Note on A2: Location of task in ProjeX sheet
Note on B1: Starting date of Project
Note on B2: Task start
Note on C1: Ending date of Project
Note on C2: Task end
Note on D2: Task duration
Note on E2: Earliest start
Note on F2: Latest start
Note on G2: Earliest finish
Note on H2: Latest finish
Note on I2: Float

## Initial Proposal_TPs (hidden)
18
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  |  | 3 | 38196 | 38225 | 0 | 460.5 | 730.5 | 213.9
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 460.5 | 514.5 | 226.9688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 532.5 | 541.5 | 239.7188
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 541.5 | 577.5 | 252.4688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 577.5 | 613.5 | 265.2188
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 613.5 | 658.5 | 277.9688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 658.5 | 712.5 | 290.7188
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 712.5 | 730.5 | 303.4688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 730.5 | 838.5 | 328.9688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 838.5 | 856.5 | 341.7188
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 1 | 1 |  | 0 | 852.78 | 860.22 | 352.875
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE | 500 | 0 | 3 | 38194 | 38203 | 0 | 442.5 | 532.5 | 150.15
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 | 0 | FALSE | 500 | 0 | 1 | 1 |  | 0 | 438.78 | 446.22 | 161.625
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 | 0 | FALSE | 500 | 0 | 2 | 2 |  | 0 | 451.5 | 460.5 | 175.9688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 460.5 | 514.5 | 188.7188
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  | 1 | 2 | 2 |  | 0 | 514.5 | 532.5 | 201.4688
0 | 1 | 1 | 24 | 24 | 24 | 24 | 24 | -24 | -24 | 0 | 0 | 0 |  | FALSE |  |  | 3 | 38226 | 38240 | 0 | 730.5 | 865.5 | 315.9
Note on A1: Last row in this sheet with a task
Note on A2: How the task is defined; 0: start and duration; 1: start and end; 2: user defined
Note on B2: Use dependants to calculate task starts (if set to 1)
Note on C2: Specify colour of Gantt bar, blank to use defaults
Note on D2: Work hours of task, 0 : 24/7; 1 : user specified hours
Note on E2: Monday hours
Note on F2: Tuesday hours
Note on G2: Wednesday hours
Note on H2: Thursday hours
Note on I2: Friday hours
Note on J2: Saturday hours
Note on K2: Sunday hours
Note on L2: How to plot non-workdays, 0:Adjust duration and task; 1: do not adjust end; 2: Adjust neither
Note on M2: PERT formula, 0:Normal; 1: Pessimistic
Note on N2: Optimistic duration
Note on O2: Most likely duration
Note on P2: Pessimistic duration
Note on Q2: PERT variance
Note on R2: Adjust start of task to avoid weekend
Note on S2: Draw task bar through weekend
Note on T2: Colour to use when plotting in PlaneX
Note on U2: Cost of task
Note on V2: Cost period of task 0:None, 1:Total, 2:hourly, 3:daily
Note on W2: If, user defined colour, draw black bar to show completion
Note on X2: Task priority, 1 - 999
Note on Y2: Task level (for indent)
Note on Z2: Dynamic link giving the row number of the task in the ProjeX sheet
Note on AA2: Type of task/group
Note on AB2: Type of task/group
Note on AC2: param1
Note on AD2: param2
Note on AE2: param3
Note on AF2: Don't work public holidays

## Sheet1_TPs (hidden)
12
3
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 391.1298 | 427.1298 | 163.2188
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 427.1298 | 436.1298 | 175.9688
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 436.1298 | 454.1298 | 188.7188
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 454.1298 | 490.1298 | 201.4688
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 490.1298 | 517.1298 | 214.2188
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 517.1298 | 553.1298 | 226.9688
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 553.1298 | 571.1298 | 239.7188
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 571.1298 | 643.1298 | 252.4688
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 2 | 643.1298 | 661.1298 | 265.2188
0 | 0 | 24 | 24 | 24 | 24 | 24 | 24 | 24 | 2 | 1 | 657.4098 | 664.8498 | 276.375
Note on A1: Last row in this sheet with a task
Note on A2: How the task is defined; 0: start and duration; 1: start and end; 2: user defined
Note on B2: Use dependants to calculate task starts (if set to 1)
Note on C2: Specify colour of Gantt bar, blank to use defaults
Note on D2: Work hours of task, 0 : 24/7; 1 : user specified hours
Note on E2: Monday hours
Note on F2: Tuesday hours
Note on G2: Wednesday hours
Note on H2: Thursday hours
Note on I2: Friday hours
Note on J2: Saturday hours
Note on K2: Sunday hours
Note on L2: How to plot non-workdays, 0:Adjust duration and task; 1: do not adjust end; 2: Adjust neither
Note on M2: PERT formula, 0:Normal; 1: Pessimistic
Note on N2: Optimistic duration
Note on O2: Most likely duration
Note on P2: Pessimistic duration
Note on Q2: PERT variance
Note on R2: Adjust start of task to avoid weekend
Note on S2: Draw task bar through weekend
Note on T2: Colour to use when plotting in PlaneX
Note on U2: Cost of task
Note on V2: Cost period of task 0:None, 1:Total, 2:hourly, 3:daily
Note on W2: If, user defined colour, draw black bar to show completion
Note on X2: Task priority, 1 - 999
Note on Y2: Task level (for indent)
Note on Z2: Dynamic link giving the row number of the task in the ProjeX sheet
Note on AA2: Type of task/group
Note on AB2: Type of task/group
Note on AC2: param1
Note on AD2: param2
Note on AE2: param3
Note on AF2: Don't work public holidays

## PrjVac (hidden)
2003 | Default

## Initial Proposal
|  | Project | Depth Migration Proposal | [25 empty] | Legend | [10 empty] | Project Milestone
|  | Starting Date | 2004-07-26 | [36 empty] | Uncompleted part of task
|  | Completion Date | 2004-09-10 | [36 empty] | Completed part of task
|  | Present Date | 2026-07-30 20:24 | [36 empty] | Overdue part of task
| Task | P | Starting | Ending | % | No. of | 2004-07-26 | [5 empty] | 2004-08-01 | [30 empty] | 2004-09-01
ID | Description |  | Date | Date | Comp. | Days | 2004-07-26 | 2004-07-27 | 2004-07-28 | 2004-07-29 | 2004-07-30 | 38199 | 38200 | 2004-08-02 | 2004-08-03 | 2004-08-04 | 2004-08-05 | 2004-08-06 | 38206 | 38207 | 2004-08-09 | 2004-08-10 | 2004-08-11 | 2004-08-12 | 2004-08-13 | 38213 | 38214 | 2004-08-16 | 2004-08-17 | 2004-08-18 | 2004-08-19 | 2004-08-20 | 38220 | 38221 | 2004-08-23 | 2004-08-24 | 2004-08-25 | 2004-08-26 | 2004-08-27 | 38227 | 38228 | 2004-08-30 | 2004-08-31 | 2004-09-01 | 2004-09-02 | 2004-09-03 | 38234 | 38235 | 2004-09-06 | 2004-09-07 | 2004-09-08 | 2004-09-09 | 2004-09-10 | 38241 | 38242
i |  | p |  |  | 11 | 1 | 2004-07-26 | 2004-07-27 | 2004-07-28 | 2004-07-29 | 2004-07-30 | 38199 | 38200 | 2004-08-02 | 2004-08-03 | 2004-08-04 | 2004-08-05 | 2004-08-06 | 38206 | 38207 | 2004-08-09 | 2004-08-10 | 2004-08-11 | 2004-08-12 | 2004-08-13 | 38213 | 38214 | 2004-08-16 | 2004-08-17 | 2004-08-18 | 2004-08-19 | 2004-08-20 | 38220 | 38221 | 2004-08-23 | 2004-08-24 | 2004-08-25 | 2004-08-26 | 2004-08-27 | 38227 | 38228 | 2004-08-30 | 2004-08-31 | 2004-09-01 | 2004-09-02 | 2004-09-03 | 38234 | 38235 | 2004-09-06 | 2004-09-07 | 2004-09-08 | 2004-09-09 | 2004-09-10 | 38241 | 38242
1.0 | Pre-processing | 13
1.1 | Data delivery | 14 | 2004-07-26 | 2004-07-26 | 0 | 0
1.2 | Data loading | 15 | 2004-07-27 | 2004-07-27 | 0 | 1
1.3 | Initial processing & velocity picking | 16 | 2004-07-28 | 2004-08-02 | 0 | 4
1.4 | Demultiple work | 17 | 2004-08-03 | 2004-08-04 | 0 | 2
2.0 | Model Building | 2 |  |  | 2004-07-28 | 2004-08-26
2.1 | Generate initial model | 3 | 2004-07-28 | 2004-08-02 | 0 | 4
2.2 | Run initial migration velocity analysis | 4 | 2004-08-05 | 2004-08-05 | 0 | 1
2.3 | Update velocity model | 5 | 2004-08-06 | 2004-08-09 | 0 | 2
2.4 | Run 1st iteration migration velocity analysis | 6 | 2004-08-10 | 2004-08-13 | 0 | 4
2.5 | Update velocity model | 7 | 2004-08-14 | 2004-08-18 | 0 | 3
2.6 | Run 2nd iteration migration velocity analysis | 8 | 2004-08-19 | 2004-08-24 | 0 | 4
2.7 | Finalize velocity model | 9 | 2004-08-25 | 2004-08-26 | 0 | 2
3.0 | Produce Final Product | 18 |  |  | 2004-08-27 | 2004-09-10
3.1 | Run full migration | 10 | 2004-08-27 | 2004-09-07 | 0 | 8
3.2 | Produce final product for client | 11 | 2004-09-08 | 2004-09-09 | 0 | 2
3.3 | Deliver final product | 12 | 2004-09-10 | 2004-09-10 | 0 | 0

## Sheet1
| Project | Depth Migration Proposal | [11 empty] | Legend | [10 empty] | Project Milestone
| Starting Date | 2004-07-15 13:01 | [22 empty] | Uncompleted part of task
| Completion Date | 2004-08-14 13:01 | [22 empty] | Completed part of task
| Present Date | 2026-07-30 20:24 | [22 empty] | Overdue part of task
Task | P | Starting | Ending | % | No. of | 2004-07-15 | [16 empty] | 2004-08-01
Description |  | Date | Date | Comp. | Days | 2004-07-15 | 2004-07-16 | 38185 | 38186 | 2004-07-19 | 2004-07-20 | 2004-07-21 | 2004-07-22 | 2004-07-23 | 38192 | 38193 | 2004-07-26 | 2004-07-27 | 2004-07-28 | 2004-07-29 | 2004-07-30 | 38199 | 38200 | 2004-08-02 | 2004-08-03 | 2004-08-04 | 2004-08-05 | 2004-08-06 | 38206 | 38207 | 2004-08-09 | 2004-08-10 | 2004-08-11 | 2004-08-12 | 2004-08-13 | 38213 | 38214 | 2004-08-16 | 2004-08-17 | 2004-08-18
| p |  |  | 10 | 1 | 2004-07-15 | 2004-07-16 | 38185 | 38186 | 2004-07-19 | 2004-07-20 | 2004-07-21 | 2004-07-22 | 2004-07-23 | 38192 | 38193 | 2004-07-26 | 2004-07-27 | 2004-07-28 | 2004-07-29 | 2004-07-30 | 38199 | 38200 | 2004-08-02 | 2004-08-03 | 2004-08-04 | 2004-08-05 | 2004-08-06 | 38206 | 38207 | 2004-08-09 | 2004-08-10 | 2004-08-11 | 2004-08-12 | 2004-08-13 | 38213 | 38214 | 2004-08-16 | 2004-08-17 | 2004-08-18
Model Building | 2
Generate initial model | 3 | 2004-07-15 13:01 | 2004-07-18 13:01 | 0 | 4
Run initial migration velocity analysis | 4 | 2004-07-19 13:01 | 2004-07-19 13:01 | 0 | 1
Update velocity model | 5 | 2004-07-20 13:01 | 2004-07-21 13:01 | 0 | 2
Run 1st iteration migration velocity analysis | 6 | 2004-07-22 13:01 | 2004-07-25 13:01 | 0 | 4
Update velocity model | 7 | 2004-07-26 13:01 | 2004-07-28 13:01 | 0 | 3
Run 2nd iteration migration velocity analysis | 8 | 2004-07-29 13:01 | 2004-08-01 13:01 | 0 | 4
Finalize velocity model | 9 | 2004-08-02 13:01 | 2004-08-03 13:01 | 0 | 2
Run full migration | 10 | 2004-08-04 13:01 | 2004-08-11 13:01 | 0 | 8
Produce final product for client | 11 | 2004-08-12 13:01 | 2004-08-13 13:01 | 0 | 2
Deliver final product | 12 | 2004-08-14 13:01 | 2004-08-14 13:01 | 0 | 0
Formulas:
Depth Migration Proposal = [Depth Migration Proposal, row above]+1